## Gantt Chart
PUCKFish Development Schedule |  |  |  |  | https://bit.ly/3m5tJ8R
PROJECT |  |  | START DATE
PUCKFish |  |  | 2021-12-01 |  |  | <-- Enter initial Start Date to populate Timeline dates.
[6 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20 |  |  |  |  | Wk 21 |  |  |  |  | Wk 22 |  |  |  |  | Wk 23
TASKS | TASK OWNER | STATUS | START | END | DAYS | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-10 | 2022-01-11 | 2022-01-12 | 2022-01-13 | 2022-01-14 | 2022-01-17 | 2022-01-18 | 2022-01-19 | 2022-01-20 | 2022-01-21 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | STATUS
Test 2.1: IMU Proof of Concept |  | Complete | 2021-10-01 | 2021-12-02 | 45 | A | A | A | A | [111 empty] | Not Started
Construct IMU Testbed |  | Complete | 2021-10-02 | 2021-10-30 | 20 | [115 empty] | In Progress
Develop IMU Electronics |  | Complete | 2021-09-02 | 2021-09-02 | 1 | [115 empty] | Complete
Run Preliminary Current Testing |  | Complete | 2021-11-30 | 2021-11-30 | 1 |  | A | [113 empty] | On Hold
Assessment and Path Forward |  | Complete | 2021-12-01 | 2021-12-02 | 2 |  |  | A | A | [111 empty] | Overdue
Test 3.1: Port and Enclosure Testing |  | Overdue | 2021-12-02 | 2022-02-10 | 51 |  |  |  | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Develop and Design Enclosure Testing for Full Depth |  | Complete | 2021-12-02 | 2021-12-18 | 12 |  |  |  | A | A | A | A | A | A | A | A | A | A | A | A
Develope and Design Sensor Ports |  | Complete | 2021-12-02 | 2021-12-18 | 12 |  |  |  | A | A | A | A | A | A | A | A | A | A | A | A
Internal Design Review |  | Complete | 2022-01-20 | 2022-01-20 | 1 | [38 empty] | A
Manufacture Enclosure |  | In Progress | 2022-01-21 | 2022-01-28 | 6 | [39 empty] | A | A | A | A | A | A
Manufacture Sensor Ports |  | In Progress | 2022-01-21 | 2022-01-28 | 6 | [39 empty] | A | A | A | A | A | A
Integration: Sensor Ports and Enclosure |  | Overdue | 2022-01-28 | 2022-02-04 | 6 | [44 empty] | A | A | A | A | A | A
Testing Plan |  | Complete | 2022-02-04 | 2022-02-06 | 1 | [49 empty] | A
Depth Proof Test |  | On Hold | 2022-02-06 | 2022-02-10 | 4 | [50 empty] | A | A | A | A
Test 2.2: Sensor Array Test |  | In Progress | 2021-10-02 | 2022-03-18 | 120 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | [35 empty] | Needs Update
Select Sensors |  | Complete | 2021-10-02 | 2021-12-03 | 45 | A | A | A | A | A | [110 empty] | Canceled
Complete Electronics Design |  | Complete | 2021-11-15 | 2021-12-16 | 24 | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Internal Design Review |  | Complete | 2021-12-16 | 2021-12-16 | 1 | [13 empty] | A
Testing Plan |  | Complete | 2021-12-16 | 2021-12-17 | 2 | [13 empty] | A | A
Functional Testing |  | Complete | 2022-01-20 | 2022-01-22 | 2 | [38 empty] | A | A
In-Water Test |  | On Hold | 2022-03-16 | 2022-03-18 | 3 | [77 empty] | A | A | A
Data Analysis |  | Canceled | 2022-01-24 | 2022-01-26 | 3 | [40 empty] | A | A | A
Iteration Time |  | On Hold | 2022-03-21 | 2022-02-23 | -19
In-Water Test 2 |  | Canceled | 2022-01-27 | 2022-01-28 | 2 | [43 empty] | A | A
Test 3.2: Full Hardware Test |  | Overdue | 2022-01-28 | 2022-03-22 | 38 | [44 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Develope and Design PUCKFish Computer |  | Complete | 2022-01-28 | 2022-02-06 | 6 | [44 empty] | A | A | A | A | A | A
Develope and Design PUCKFish Power Supply |  | Complete | 2022-01-28 | 2022-02-06 | 6 | [44 empty] | A | A | A | A | A | A
Internal Design Review |  | Complete | 2022-02-04 | 2022-02-04 | 1 | [49 empty] | A
Testing Plan: Functionality |  | In Progress | 2022-03-18 | 2022-03-21 | 2 | [79 empty] | A
Testing Plan: Battery Life Test |  | In Progress | 2022-03-18 | 2022-03-21 | 2 | [79 empty] | A
Functionality and Battery Life Test |  | On Hold | 2022-03-22 | 2022-03-22 | 1
Test 4: Full PUCKFish Functionality Testing |  | Overdue | 2022-03-21 | 2022-04-30 | 30
Final Iteration and Adjustments |  | Overdue | 2022-03-22 | 2022-03-31 | 8 | [81 empty] | A | A | A | A | A | A | A | A
Testing Plan: Full Functionality Testing |  | On Hold | 2022-03-21 | 2022-03-27 | 5 | [80 empty] | A | A | A | A | A
Full Functionality Test |  | On Hold | 2022-03-31 | 2022-04-01 | 2 | [88 empty] | A | A
Testing Review |  | On Hold | 2022-04-01 | 2022-04-02 | 1 | [89 empty] | A
Iteration and Adjustements |  | On Hold | 2022-04-02 | 2022-04-29 | 20 | [90 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Optional 2nd Functionality Test |  | Canceled | 2022-04-29 | 2022-04-30 | 1 | [109 empty] | A
Final Administrative Items |  | On Hold | 2022-04-30 | 2022-05-18 | 13 | [110 empty] | A | A | A | A | A
Customer Installation |  | On Hold | 2022-04-30 | 2022-05-18 | 13 | [110 empty] | A | A | A | A | A
ECE Day |  | On Hold | 2022-05-06 | 2022-05-06 | 1 | [114 empty] | A
Promotional Event |  | On Hold | 2022-04-19 | 2022-04-21 | 3
Test 2.2: Sensor Array Test |  | In Progress | 2021-10-02 | 2022-01-28 | 85
Select Sensors |  | In Progress | 2021-10-02 | 2021-12-03 | 45
Complete Electronics Design |  | On Hold | 2021-11-15 | 2021-12-14 | 22
Functional Testing |  | On Hold | 2021-12-14 | 2021-12-15 | 2
In-Water Test |  | On Hold | 2021-12-15 | 2021-12-16 | 2
Data Analysis |  | On Hold | 2021-12-16 | 2021-12-18 | 2
Iteration Time |  | On Hold | 2022-01-20 | 2022-01-27 | 6
In-Water Test 2 |  | On Hold | 2022-01-27 | 2022-01-28 | 2
Test 3.2: Full Hardware Test |  | On Hold | 2022-01-28 | 2022-02-10 | 10
Develope and Design PUCKFish Computer |  | On Hold | 2022-01-28 | 2022-02-04 | 6
Develope and Design PUCKFish Power Supply |  | On Hold | 2022-01-28 | 2022-02-04 | 6
Internal Design Review |  | On Hold | 2022-02-04 | 2022-02-04 | 1
Testing Plan: Functionality |  | On Hold | 2022-02-04 | 2022-02-06 | 1
Testing Plan: Battery Life Test |  | On Hold | 2022-02-04 | 2022-02-06 | 1
Functionality and Battery Life Test |  | On Hold | 2022-02-06 | 2022-02-10 | 4
Test 3.1: Port and Enclosure Testing |  | In Progress | 2021-12-02 | 2022-02-10 | 51
Develop and Design Enclosure Testing for Full Depth |  | In Progress | 2021-12-02 | 2021-12-18 | 12
Internal Design Review |  | On Hold | 2022-01-20 | 2022-01-20 | 1
Manufacture Enclosure |  | On Hold | 2022-01-21 | 2022-01-28 | 6
Develope and Design Sensor Ports |  | On Hold | 2021-12-02 | 2021-12-18 | 12
Internal Design Review |  | On Hold | 2022-01-21 | 2022-01-28 | 6
Manufacture Sensor Ports |  | On Hold | 2022-01-20 | 2022-01-28 | 7
Integration: Sensor Ports and Enclosure |  | On Hold | 2022-01-28 | 2022-02-04 | 6
Testing Plan |  | On Hold | 2022-02-04 | 2022-02-06 | 1
Depth Proof Test |  | On Hold | 2022-02-06 | 2022-02-10 | 4

## BLANK - Gantt Chart
GANTT CHART TEMPLATE IN GOOGLE SHEETS
PROJECT |  |  | START DATE
|  |  | 2025-09-02 |  |  | <-- Enter initial Start Date to populate Timeline dates.
User to complete non-shaded fields only. | [5 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
TASKS | TASK OWNER | STATUS | START DATE | END DATE | DAYS | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | STATUS
Phase 1: Assess the Need |  |  | 0 | 0 | 0 | [100 empty] | Not Started
Clearly identify the problem and solution |  |  |  |  | 0 | [100 empty] | In Progress
Research existing alternatives |  |  |  |  | 0 | [100 empty] | Complete
Pinpoint gaps in existing products or services |  |  |  |  | 0 | [100 empty] | On Hold
Determine skills, equipment, and materials needed |  |  |  |  | 0 | [100 empty] | Overdue
Decide whether to proceed |  |  |  |  | 0 | [100 empty] | Needs Review
Phase 2: Find Opportunity and Check Viability |  |  | 0 | 0 | 0 | [100 empty] | Needs Update
Define your mission |  |  |  |  | 0 | [100 empty] | Canceled
Research market |  |  |  |  | 0
Conduct interviews with stakeholders and SMEs |  |  |  |  | 0
Identify needed resources |  |  |  |  | 0
Identify startup costs |  |  |  |  | 0
Identify operating costs |  |  |  |  | 0
Determine sources of funding |  |  |  |  | 0
Assess profitability |  |  |  |  | 0
Phase 3: Evaluate Potential Risks |  |  | 0 | 0 | 0
Assess market size |  |  |  |  | 0
Estimate competition |  |  |  |  | 0
Conduct SWOT Analysis |  |  |  |  | 0
Assess economic climate |  |  |  |  | 0
Develop strategic plan |  |  |  |  | 0
Phase 4: Attract Stakeholders |  |  | 0 | 0 | 0
Establish management team |  |  |  |  | 0
Seek strategic partnerships |  |  |  |  | 0
Develop outreach plan |  |  |  |  | 0
Phase 5: Prepare and Pitch Business Plan |  |  | 0 | 0 | 0
Create business plan outline |  |  |  |  | 0
Fill in each section of business plan |  |  |  |  | 0
Develop investor pitch deck |  |  |  |  | 0
Phase 6: Establish Supporting Systems |  |  | 0 | 0 | 0
Create bookkeeping systems |  |  |  |  | 0
Create Manuals and Policies |  |  |  |  | 0
Create company portal to store key documents |  |  |  |  | 0

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.